## Quantitative Risk Analysis
DECISION TABLE
Coefficient of Realism | 0.8 |  | Favorable Market Probability Value |  | 0.78
The best (for Favorable Market) | 300000 |  | Unfavorable Market Probability Value |  | 0.22
The best (for Unfavorable Market) | 0
Alternative | State of Nature |  | Decision Making under Uncertainty |  |  |  |  | Decision Making under Risk
| Favorable Market | Unfavorable Market | Optimistic Criterion | Pessimistic Criterion | Hurwicz Criterion | Laplace Criterion | Minimax Regret | EMV | EVwPI | EVPI | EOL
Release in January 2022 | 300000 | -170000 | 300000 | -170000 | 206000 | 235000 | 170000 | 196600 | 234000 | 37400 | 37400
Release in February 2022 | 200000 | -200000 | 200000 | -200000 | 120000 | 200000 | 200000 | 112000 |  |  | 122000
Release in March 2022 | 150000 | -225000 | 150000 | -225000 | 75000 | 187500 | 225000 | 67500 |  |  | 166500
Cancel project | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 |  |  | 234000
Opportunity Loss Table
Alternative | State of Nature
| Favorable Market | Unfavorable Market
Release in January 2022 | 0 | 170000
Release in February 2022 | 100000 | 200000
Release in March 2022 | 150000 | 225000
Cancel project | 300000 | 0
BAYESIAN ANALYSIS
Positive
Real Market Condition | State of Nature |  |  | State of Nature | Conditional Probability | Prior Probability | Posterior Probability
| Favorable Market | Unfavorable Market |  |  |  |  | Joint Probability | P(State of Nature ¦ Positive)
Positive | 0.7 | 0.2 |  | Favorable Market | 0.7 | 0.5 | 0.35 | 0.77778
Negative | 0.3 | 0.8 |  | Unfavorable Market | 0.2 | 0.5 | 0.1 | 0.22222
Total | 1 | 1 |  |  |  |  | 0.45 | 1
Negative
|  |  |  | State of Nature | Conditional Probability | Prior Probability | Posterior Probability
[7 empty] | Joint Probability | P(State of Nature ¦ Positive)
|  |  |  | Favorable Market | 0.3 | 0.5 | 0.15 | 0.27273
|  |  |  | Unfavorable Market | 0.8 | 0.5 | 0.4 | 0.72727
[7 empty] | 0.55 | 1
PERT/CPM
Activity | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | On Critical Path | Project Mean | Project Variance
Project Initialization | 5 | 10 | 15 | 10 | 2.7778 | 1 | 10 | 2.7778
Application Design | 7 | 14 | 28 | 16 | 12.25 | 1 | 16 | 12.25
Develop Prototype | 14 | 21 | 30 | 22 | 7.1111 | 0 | 0 | 0
Develop Alpha Version | 7 | 14 | 21 | 14 | 5.4444 | 0 | 0 | 0
Alpha Testing | 3 | 7 | 14 | 8 | 3.3611 | 1 | 8 | 3.3611
Develop Beta Version | 7 | 21 | 30 | 21 | 14.6944 | 0 | 0 | 0
Beta Testing | 7 | 10 | 21 | 12 | 5.4444 | 1 | 12 | 5.4444
Deployment | 3 | 7 | 10 | 7 | 1.3611 | 0 | 0 | 0
|  |  |  | 110 |  |  | 46 | 23.8333
| z | pdf
| 21 | 0.009656
| 22 | 0.010082
| 23 | 0.010507
| 24 | 0.010932
| 25 | 0.011354
| 26 | 0.011771
| 27 | 0.012182
| 28 | 0.012585
| 29 | 0.012979
| 30 | 0.013362
| 31 | 0.013731
| 32 | 0.014086
| 33 | 0.014425
| 34 | 0.014746
| 35 | 0.015048
| 36 | 0.015328
| 37 | 0.015587
| 38 | 0.015822
| 39 | 0.016032
| 40 | 0.016217
| 41 | 0.016375
| 42 | 0.016505
| 43 | 0.016607
| 44 | 0.01668
| 45 | 0.016724
| 46 | 0.016739
| 47 | 0.016724
| 48 | 0.01668
| 49 | 0.016607
| 50 | 0.016505
| 51 | 0.016375
| 52 | 0.016217
| 53 | 0.016032
| 54 | 0.015822
| 55 | 0.015587
| 56 | 0.015328
| 57 | 0.015048
| 58 | 0.014746
| 59 | 0.014425
| 60 | 0.014086
| 61 | 0.013731
| 62 | 0.013362
| 63 | 0.012979
| 64 | 0.012585
| 65 | 0.012182
| 66 | 0.011771
| 67 | 0.011354
| 68 | 0.010932
| 69 | 0.010507
| 70 | 0.010082
| 71 | 0.009656